## Overall
Task Number | Task | Time to Complete (Hours)
1 | Build a portal to allow users to sign in to Shopify and Square
2 | Set up O-auth for store owners
3 | Choose O-auth mechanism | 0.5
4 | Read documentation | 1
5 | Set up O-auth | 4
6 | Set up Shopify authorization
7 | Read documentation | 1
8 | Set up authorization to connect to Shopify store | 5
9 | Set up Square authorization
10 | Read documentation | 1
11 | Set up authorization to connect to square reader | 5
12 | Build web app that provides a UI for users to connect to both platforms
13 | Decide what frameworks to build frontend in | 0.5
14 | Design frontend of the application | 3
15 | Stand up server to be the backend for the website | 5
16 | Set up database
17 | Decide which language to build database in | 0.5
18 | Set up database framework | 3
19 | Set up database for customers | 3
20 | Send information from Square to Shopify
21 | Push information from Square to the database | 6
22 | Query information from the database into Shopify | 6
23 | Email customers.
24 | Design email to be sent out | 1
25 | For every transaction, email customers a receipt and a thank you. | 3
26 | For every new customer, email customers a receipt, thank you, and a link to create an account on the store's online page. | 2
| Total Time | 50.5

## Shoki
Tasks | Time Estimation
Set up OAuth to login to our platform | 5
Set up an authetication system to create and manage all of the accounts | 20
Have an API from Square to retrieve transactional data and customer info | 10
Import transactional and customer info into store owner's shopify account | 30
Properly track sales in Shopify | 10
Setting up a database to store transactional history and customer info | 20
Set up a website for the platform | 50
Set up a backend server to process the data | 5
Total | 150

## Minh
Task Number | Task Name | Desc. | Estimation (Hours)
1 | Login/Signup Screen | Login/Signup with OAuth | 12
2 | Integrate Shopify/Square accounts | Add way for store to login to Square/Shopify | 40
3 | Database | Transaction schema for customer phone, email, name, Square transaction id | 12
4 | Front Facing/Customer view | Logic to lead customer to payment page, then to page to prompt for name/email/phone number | 24
5 | Customer info to Shopify Acct | Use transaction id to look up transaction from square. Push this info + customer email/phone to Shopify | 24
6 | Set up back end server |  | 12
124

## Daniela
Task Number | Task | Description | Time
1 | Log in or signup | Use OAuth to login or signup | 6
2 | Read documentation on Shopify and Square | Figure out how the two APIs work and how to start integrating them | 5
3 | Database | Create two databases, one for the owners and one for the customers | 3
4 | Customers view | Create a way for the customer to input their email/phone, and design what they would see | 6
5 | Transaction | Using the transaction id, find the information of the customer (what they bought) and then push that information into the Shopify account, where the owner can see it too | 7
6 | Email | Send out thank you email to the customer | 1
28

## Jonathan
Create a page with forms for the store to create an app account and sign in. The app account will contain their Shopify and Square account info.
Create display. | 5
Configure APIs. (Figure out how to get and post info.) | 5
Log Square transactions into Shopify sales history.
Access Shopify sales table. | 1
Add purchase info to existing customer accounts. | 4
Create accounts for new customers. | 2
Email customers.
For every transaction, email customers a receipt and a thank you. | 3
For every new customer, email customers a receipt, thank you, and a link to create an account on the store's online page. | 2
Total: 22 hours

## Sarah
Task Number | Task | Time to Complete (Hours)
1 | Build a portal to allow users to sign in to Shopify and Square
2 | Set up O-auth for store owners
3 | Choose O-auth mechanism | 0.5
4 | Read documentation | 1
5 | Set up O-auth | 4
6 | Set up Shopify authorization
7 | Read documentation | 1
8 | Set up authorization to connect to Shopify store | 5
9 | Set up Square authorization
10 | Read documentation | 1
11 | Set up authorization to connect to square reader | 5
12 | Build web app that provides a UI for users to connect to both platforms
13 | Decide what frameworks to build frontend in | 0.5
14 | Design frontend of the application | 3
15 | Stand up server to be the backend for the website | 5
16 | Set up database
17 | Decide which language to build database in | 0.5
18 | Set up database framework | 3
19 | Set up database for customers | 3
20 | Send information from Square to Shopify
21 | Push information from Square to the database | 6
22 | Query information from the database into Shopify | 6
23 | Design Email to be sent out | 1
| Total Time | 45.5